## Tasks
PROJECT TASKS (Edit this table)
Task | Start | Finish | Duration_days | Resource | Start_offset | Project Start | 2015-07-13
Acquisition | 2015-07-13 | 0 | 25 | Carole Poland | 0 | Project Finish | 2015-10-22
Manuscript received | 2015-07-13 | 2015-07-13 | 0 | Carole Poland | 0
Content edit | 2015-07-13 | 2015-08-07 | 25 | Carole Poland | 0
Handoff to Editorial | 2015-08-14 | 2015-08-14 | 0 | Robin Wood | 32
Organize manuscript | 2015-08-17 | 2015-08-22 | 5 | Robin Wood | 35
Copyedit | 2015-08-24 | 2015-09-13 | 20 | Copyeditors | 42
Cover design | 2015-08-17 | 2015-08-22 | 5 | William Flash | 35
Set pages | 2015-09-01 | 2015-09-11 | 10 | Katie Jordan | 50
Interior illustration | 2015-09-07 | 2015-09-22 | 15 | William Flash | 56
Pages review | 2015-10-12 | 2015-10-22 | 10 | John Evans | 91
Formulas:
Finish = [Start]+[Duration_days]

## Resources
Resource Name | Type | Max Units | Std Rate | Cost/Use | Accrual | Base
Carole Poland | Work | 100% | $0.00/hr | $0.00 | Prorated | Standard
Color Setting Services | Work | 100% | $0.00/hr | $0.00 | Prorated | Standard
Copyeditors | Work | 100% | $0.00/hr | $0.00 | Prorated | Standard
John Evans | Work | 100% | $20.00/hr | $0.00 | Prorated | Standard
Katie Jordan | Work | 100% | $0.00/hr | $0.00 | Prorated | Standard
Printing Service | Work | 100% | $0.00/hr | $0.00 | Prorated | Standard
Robin Wood | Work | 100% | $0.00/hr | $0.00 | Prorated | Standard
William Flash | Work | 100% | $55.00/hr | $0.00 | Prorated | Standard

## Gantt
Gantt Chart
Task | Start Offset (days) | Duration (days)
Acquisition | 0 | 25
Manuscript received | 0 | 0
Content edit | 0 | 25
Handoff to Editorial | 32 | 0
Organize manuscript | 35 | 5
Copyedit | 42 | 20
Cover design | 35 | 5
Set pages | 50 | 10
Interior illustration | 56 | 15
Pages review | 91 | 10

## Calendar
Task | Start | Finish | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17 | 2015-07-18 | 2015-07-19 | 2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-25 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-01 | 2015-08-02 | 2015-08-03 | 2015-08-04 | 2015-08-05 | 2015-08-06 | 2015-08-07 | 2015-08-08 | 2015-08-09 | 2015-08-10 | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-15 | 2015-08-16 | 2015-08-17 | 2015-08-18 | 2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-22 | 2015-08-23 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-29 | 2015-08-30 | 2015-08-31 | 2015-09-01 | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22
Acquisition | 2015-07-13 | 2015-08-07
Manuscript received | 2015-07-13 | 2015-07-13
Content edit | 2015-07-13 | 2015-08-07
Handoff to Editorial | 2015-08-14 | 2015-08-14
Organize manuscript | 2015-08-17 | 2015-08-22
Copyedit | 2015-08-24 | 2015-09-13
Cover design | 2015-08-17 | 2015-08-22
Set pages | 2015-09-01 | 2015-09-11
Interior illustration | 2015-09-07 | 2015-09-22
Pages review | 2015-10-12 | 2015-10-22

## Timeline
Milestone | Date
Acquisition | 2015-07-13 | 1
Editorial | 2015-08-17 | 1
Pages review | 2015-10-12 | 1
Color prep & printing | 2015-10-26 | 1
Tip: In Excel, right-click the timeline points → Add Data Labels → Value From Cells → choose milestone names in A2:A6. | 2015-10-22 | 1